## Time Estimates
Stage | Action | Time Estimate
1. Research planning | Call for research in Slack + monitoring | 1 hour |  | 15
1. Research planning | Prepare research questions | 1 hour |  | 60
1. Research planning | Conference w/ stakeholders | 1 hour |  | 60
2. Material preparation | Preparing Calendly event / coordinating calendars | 45 minutes |  | 45
2. Material preparation | Prepare screens/prototypes | 1 hour |  | 60
2. Material preparation | Write interview protocol | 2 hours |  | 120
2. Material preparation | Review protocol w/ stakeholders | 1 hour |  | 60
3. Participant recruitment | Recruitment (10 emails) | 45 minutes |  | 45
3. Participant recruitment | Confirm attendance / check on NDAs | 30 minutes |  | 30
4. Interviews | Conduct interviews | 1.5 hours each | 5 | 450
4. Interviews | File management | 1 hour |  | 30
5. Analysis & synthesis | Analyze transcripts | 6 hours |  | 360
5. Analysis & synthesis | Synthesize insights | 3-4 hours |  | 180
5. Analysis & synthesis | Discuss insights w/ stakeholders | 1 hour |  | 60
6. Reporting | Prep report | 3.5 hours |  | 210
6. Reporting | Finalize & share report | 30 minutes |  | 30
|  |  |  | 1815 | 30.25
Research Planning |  | 3 hours | 3
Material Preparation |  | 4 hours 45 min. | 5
Participant Recruitment |  | 1.5 hours | 1.5
Interviews (5) |  | 6 | 6
Analysis & Synthesis |  | 9 hours | 9
Reporting |  | 4 hours | 4

## Sheet4
Process | Step | Link(s) | Notes
Recruitment | Receive short list from Billy/Meredith
Confirm calendly times
| Send recruitment emails |  | Use Gmail Templates (Growth/Learning) Update names/email addresses to send Potentially: overrecruit to ensure 5 sessions completed
| Track session sign ups / NDA signatures | Participant Tracking NDA
Calendaring | Duplicate scheduled sessions in Google Calendar
| Invite stakeholders to sessions, once scheduled |  | Use the duplicated event, to reduce visibility for participants. Book UX Lab for session.
Update Google calendar in Duo to reflect outside projects
Update Outlook calendars to reflect Duo projects
File Management | After sessions, download Zoom interviews
| Upload interviews to Reduct.video | Reduct.live
| Update names to include participant name, content, and area |  | Ex. "Jason: Widgets & Quests (Growth)"
Communication | Follow thread for research requests on Slack |  | Billy/Meredith typically post the request at the beg. of week
| Add threads for each participant 15 min. before session |  | These can be pre-schedule once sessions are set up using the post scheduling feature in Slack.
Protocol Prep | Call for research in Slack
Prepare research questions
Conference w/ stakeholders
| Write interview protocol (draft) | Discussion Guide Template
Review protocol w/ stakeholders
Prepare stimuli
Analysis & Reporting | Analyze transcripts / recordings
Create clips, as needed
Synthesize insights
Discuss insights w/ stakeholders
Prep report
Finalize & share report

## Tools
Duolingo Time Tracking
MONDAY | 6 |  | Reporting | Prep for new week | Calendaring & Recruitment | Admin
TUESDAY | DAY OFF
WEDNESDAY | 6 |  | Protocol Prep | Mtgs. w/ Stakeholders
THURSDAY | 9 |  | Interviews | Note Taking | Debriefs
FRIDAY | 3 |  | Interviews | Note Taking | Debriefs | Analysis | Admin
SATURDAY | DAY OFF
SUNDAY | 6 |  | Analysis | Creating Clips Etc. | Reporting
30
| MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
8 | 1 | 1 | 1 | 1 | 1
9 | 1 | 1 | 1 | 1 | 1
10 | 1 | 1 | 1 | 1 | 1
11 | 1 | 1 | 1 | 1 | 1
12 | 1 | 1 | 1 | 1 | 1 |  | 1
13 | SACRED LUNCH HOUR
14 | 1 | 1 | 1 | 1 | 1 |  | 1
15 | 1 | 1 | 1 | 1 | 1 |  | 1
16 | 1 | 1 | 1 | 1 | 1 |  | 1
17 | 1 | 1 | 1 | 1 | 1 |  | 1
18 | 1 | 1 | 1 | 1 | 1 |  | 1

## Action Items Calendar
DUOLINGO TASKS
Monday |  | Tuesday |  | Wednesday |  | Thursday |  | Friday |  | Weekend
Check Recruitment Emails | 0.5 | Copy Protocol/Report Templates | 0.5 | Schedule Session Threads | 0.5 | Final prep for sessions | 6 | Check Calendly / Confirm Schedule | 0.5 | Run through interviews 1-2 | 1.5
Review highlights in Reduct | 1 | Update Participant List | 0.5 | Flesh out protocol draft | 1 | Conduct interviews |  | Schedule Recruitment Emails | 0.5 | Highlight as needed
Compile Notes / Upload to RR Repository | 1 | Follow-up w/ Stakeholders | 0.5 | Send protocol for approval |  | Post session summaries |  | Schedule Call for Research | 0.5 | Run through interviews 3-4 | 1.5
Write Draft | 1 | Bare bones Protocol Draft | 1.5 | Update session files, as needed | 2 | Headstart on Friday, if feasible | 0.5 | Upload Recordings to Reduct | 0.5 | Highlight as needed
Run through ChatGPT | 0.5 | Review additional asks |  |  |  | Update Report Draft |  | Headstart on highlights, time permitting |  | Run through interviews 5-6 | 1.5
Revise as needed | 0.5 | Send out 2nd round recruitment | 1 |  |  |  |  | Conduct interview, if needed | 1 | Highlight as needed
Share Report by EOD | [7 empty] | Update Participant List | 0.5
Pull clips, time permitting | 0.5 | [6 empty] | Submit Ethnio Request
Monitor threads | 0.5
Schedule stakeholder standups | 0.5
| 6 | 0 | 4 | 0 | 3.5 | 0 | 6.5 | 0 | 3.5 | 0 | 4.5
8 |  | 4 |  | 4 |  | 8 |  | 4 |  | 6
8 |  | 6 |  | 6 |  | 8 |  | 6 |  | 6
*indicates possible automation opportunity | [5 empty] | * PM full unplug from Stride
Download CSV of all sessions
Highlight & tag interviews in Reduct | --> |  | --> | Find/replace language related to Duolingo | --> | Upload into ChatGPT to create an outline | -->